## ECP Integration & Demonstration
[5 empty] | FY18 | [5 empty] | FY19 | [11 empty] | FY20
[5 empty] | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Task | Description | People | Person-Months | Dependencies | Apr. | May | Jun. | Jul. | Aug. | Sep. | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
1.1.0 | Development and verification of actuator line simulation capabilities | Maniaci
1.1.1 | Work to develop actuator line and ABL models and Nalu so it is ready for use by WD, MMC, etc.…
1.1.2 | Neutral ABL with basic statistics, Wake slices | Blaylock | bar: Q3 Apr. to Q3 May
1.1.3 | Improved DAKOTA link |  | 2 PM, quarter time | bar: Q4 Aug.
1.1.4 | Synthetic Lidar | Herges/Knaus | bar: Q3 May to Q3 Jun.
1.1.5 | Stable ABL | Blaylock |  | ABL eqn/IC/BC development
1.1.6 | Unstable ABL | Blaylock |  | ABL eqn/IC/BC development | bar: Q3 Apr. to Q3 Jun.; Q1 Dec to Q4 Sep
1.1.7 | Mesh capability for active wake steering during simulation | Lawson, Shreyas |  | Overset group. Other method for wake movement? | bar: Q1 Oct to Q3 Jun
1.1.8 | Mixed Actuator Disc/AL | Tony, Matt C | 1PM | Actuator disc capability (Actuator Disk/Line Group) | bar: Q1 Oct to Q3 Jun
1.1.9 | DAKOTA link for MLMF sampling | Frankel | 3PM, quarter time | Under WD? | bar: Q3 Apr to Q3 Jun
1.1.10 | Wind farm inflow and wake stats advanced capibilities | Shreyas
2.1.0 | Wind farm simulation demonstration | Blaylock
2.1.1 | Stable boundary layer precursor | Blaylock / Shashank / Tony | 1PM @ quarter time | ABL eqn/IC/BC development
2.1.2 | Unstable boundary layer precursor | Blaylock / Shashank / Tony | 1PM @ quarter time | ABL eqn/IC/BC development
|  | Blaylock / Shashank / Tony | 1PM @ quarter time
2.1.3 | 2-3 Turbine simulation with all 3 ABL types (Siemens 2.3 or SWiFT blades) | Ganesh / Blaylock | 2PM @ half time | Release of Siemens 2.3 geometry
2.1.4 | Full wind farm simulations with all 3 ABL | Whole team | 2PM @ half time
2.1.5 | Analyze and validate wind farm simulations | Whole team | TBD
2.1.6
3.1.0 | Blade resolved simulations | ML | Person Weeks
3.1.1 | Make determination on sliding or overset simulation capability | ML, SA | 1 | Overset team
3.1.2 | Develop single turbine mesh and test runs | ML | 4 | Release of Siemens 2.3 geometry
3.1.3 | Identify QOIs for single turbine simulation and wake | ML, SA, Mbar, MB, DM | 2
3.1.4 | Develop visualization and data processing strategy for single turbine | KG | 1
3.1.5 | Single turbine production run | ML, SA | 4 | bar: Q1 Oct
3.1.6 | Single turbine data processing and analysis | ML, SA, Mbar, DM | 4
3.1.7 | Develop two turbine mesh | ML | 6
3.1.8 | Identify QOIs for single turbine simulation and wake impingement | ML, SA, Mbar, MB, DM | 2
3.1.9 | Develop visualization and data processing strategy for single turbine | KG | 1
3.1.10 | Two turbine production runs | ML, SA | 6 | bar: Q4 Aug
3.1.11 | Two turbine data processing and analysis | ML, SA, Mbar, DM | 4
3.1.12 | NREL 5 MW data processing | ML | 4
3.1.13 | Fluid structure interactions - will we do this?
Decision on what turbine we will use
Notes: Is there a disconnect between WD and HFM/ECP? How can this be improved? A high level question for A2e management / Pis
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1

## ValidationCases
Validation cases
Initial SWiFT case | Q3 Fy18
SWiFT UQ Case | Q4 FY18
SWiFT stable case | Q2Fy18
SWiFT Unstable case | Q3FY18
SWiFT stable, active Wake steering | Q4Fy18
SWiFT MLMF statistical analysis | Q2FY19
DanAero blade?
Siemens blade?
GE?
Rodsand II
OWEZ
MEXICO
Phase VI
…